| RULE PACKAGE | NOTICE ACTION DATE | OAL FILING DATE | 45-day NOTICE DATE | PUBLIC HEARING DATE | RE-NOTICE DATE | BOF ADOPTION | FINAL OAL/NOD FILING | OAL APPROVAL DATE | CURRENT STATUS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Emergency FRE and OWE | 23-Dec-24 | 6-Jan-25 |  |  |  |  |  |  | Approved by OAL, active until 10/10/2025 |
| Forest Resilience and Oak Woodland Exemption Permanent Rulemaking |  |  | Sept 12, 2025 | Nov 4, 2025 |  | 5-Nov-25 | 19-Nov-25 |  | Approved in part by OAL, effective 1/6/2026. Canopy standards withdrawn, will resubmit. |
| Watercourse Crossings and Emergency Notice Watercourse Crossing Requirements, 2025 | 19-Jun-24 | 12-Nov-24 | 22-Nov-24 | 22-Jan-24 | 20-Jun-25 | 20-Aug-25 | 14-Oct-26 | 1-Dec-25 | Approved by OAL, effective 1/1/26 |
| 2025 Fire Risk Reduction Community List | 6-Nov-24 |  | 6-Dec-24 | 22-Jan-25 |  |  |  |  | Approved by OAL, effective 10/1/2025 |
| Less than 3-acre Conversion Exemptions | 18-Jun-25 | 24-Jun-25 | 4-Jul-25 | 20-Aug-25 |  |  |  |  | Awaiting Final OAL Submittal |
| Apprentice Professional Forester Program Proposal, 2024 | 15-May-24 | 19-Nov-24 | 6-Dec-24 | N/A |  | 5-Mar-25 |  |  | Maximum timeline exceeded, additional ISOR required |
| RULE PACKAGE | NOTICE ACTION DATE | OAL FILING DATE | 45-day NOTICE DATE | PUBLIC HEARING DATE | RE-NOTICE DATE | BOF ADOPTION | FINAL OAL/NOD FILING | OAL APPROVAL DATE | CURRENT STATUS |
| Exemption Use on Active Plans |  |  |  |  |  |  |  |  | Pending Notice Submission |
| Vegetation Treatment within the WLPZ | 6-Jun-25 | 22-May-25 |  | 24-Jul-25 |  |  |  |  | Pending Board FSOR Review |
| Utility and Public Agency ROW Exemption Amendments |  |  |  |  |  |  |  |  | Within MGMT Discussion, pending economic evaluation |
| Completion Notices for Emergency Notice Timber Operations under 14 CCR §1052 |  |  |  |  |  |  |  |  | Pending Notice Submission |
| Utility and Public Agency ROW Exemption Amendments |  |  |  |  |  |  |  |  | Within MGMT Discussion, pending economic evaluation |
| RULE PACKAGE | NOTICE ACTION DATE | OAL FILING DATE | 45-day NOTICE DATE | PUBLIC HEARING DATE | RE-NOTICE DATE | BOF ADOPTION | FINAL OAL/NOD FILING | OAL APPROVAL DATE | CURRENT STATUS |
| Ember Resistant Zone 0 |  |  |  |  |  |  |  |  | Within ZZRA Discussion |
| Points of Light 2025 |  |  |  |  |  |  |  |  | Within FPC Discussion |
| Roles and Responsibilities of LTOs |  |  |  |  |  |  |  |  | Within FPC Discussion |
| “Plan Area” Definition within the Forest Practice Rules |  |  |  |  |  |  |  |  | Within MGMT Discussion |